## Daily Plan
InnovateUS Public Engagement Coaching Tool — Daily Build Plan
Feb 9 – Mar 16, 2026 ¦ Kushal + Manan + Batuhan ¦ ~18 Working Days ¦ OpenAI GPT-4.1 + Weaviate RAG
# | Date | Day | Phase | What We Did / Do | Features | Status
1 | Feb 9 | Sun | Setup & Research | • Create Git repo & project structure • Research RAG pipeline options (Weaviate, OpenAI embeddings) • Study Rebooting Democracy codebase for adaptation • Set up .env config, .gitignore, LICENSE | Planning + research | Completed
2 | Feb 10 | Mon | Ingestion Pipeline | • Build basic public HTML chatbot UI • Create PDF ingestion pipeline (ingest-pdfs.mjs) • Set up Weaviate schema and connection • Implement LLM-based intelligent chunking strategy • Test chunking model variations | #1 Ingestion pipeline #2 Basic chatbot UI | Completed
3 | Feb 11 | Tue | Ingestion Pipeline | • Improve ingestion strategy V1 (chapter-based splitting) • Add PDF-to-Markdown conversion via Docling (convert-pdfs.py) • Implement BM25 + semantic vector search fallback • Refine Weaviate search queries | #1 Ingestion V2 | Completed
4 | Feb 17 | Mon | UI Build | • Build full React app: Home, Coach, CaseStudies, CaseStudyDetail, ChatBot, Layout • Set up Vite + Tailwind CSS + TypeScript • Create Radix UI component library (Badge, Button, Card, Dialog, Tabs, etc.) • Add React Router with all routes • Build 9-question Nesta coaching assessment UI | #3 React UI #5 Coach assessment #8 Case studies UI | Completed
5 | Feb 18 | Tue | Data Ingestion | • Build Excel ingestion pipeline (ingest.py) • Ingest Participedia case studies from Data Tracker.xlsx • Implement section-based and sliding-window chunking for Excel data • Create CaseStudyLibrary collection in Weaviate | #1 Excel pipeline #8 Case study data | Completed
6 | Feb 19 | Wed | Backend Integration | • Wire UI to backend: chatbot, coach, case studies all connected • Implement RAG agent tools (search_knowledge_base, get_document_details) • Build agent runner with function calling loop (max 5 iterations) • Add case study data from Participedia (Batuhan) • Add Weaviate MCP for Cursor integration • Fix Netlify function timeouts • Adjust chunking/tagging strategy for better retrieval | #2 RAG chatbot #4 Agent system #8 Case studies | Completed
7 | Feb 20 | Thu | Migration & Testing | • Migrate from Netlify Functions to Express server (server.mjs) • Build all API endpoints: /api/chatbot, /api/adapt-case-study, /api/generate-plan (later pivoted) • Add relevancy score metric for case studies (Manan) • Add test suite: Vitest + React Testing Library (Manan) • Rebrand UI to InnovateUS theme • Create markdown-content component for rich rendering | #11 Relevancy scoring #14 Test suite #13 InnovateUS branding | Completed
8 | Feb 23 | Fri | Refinement & Deploy | • Add search bar and topic filtering for case studies (Batuhan) • Refine case study output formatting • Set up Render deployment config (render.yaml) • Fix Render build command • Update .gitignore | #12 Search & filter #15 Deployment config | Completed
9 | Mar 3 | Mon | Coach Flow Redesign | • Redesign coach into multi-step flow: Assessment → Dashboard → Coaching → Reflection • Build AssessmentDashboard with per-question results and status tracking • Build CoachingChatPanel for per-question AI coaching conversations • Build Reflection page with PDF export (jsPDF) • Add new routes (/coach/dashboard, /coach/reflection) • Add AI evaluation endpoint (/api/evaluate-assessment) | #5 Assessment dashboard #6 Coaching chat #7 Reflection + PDF | Completed
10 | Mar 4 | Tue | Full Flow + Polish | • Polish assessment dashboard: status indicators, progress tracking • Improve coaching chat UX: conversation flow, streaming display • End-to-end test of full coaching flow: assessment → evaluation → coaching → reflection • Fix edge cases in assessment responses | UX polish | Not Started
11 | Mar 5 | Wed | Full Flow + Polish | • Polish case study adaptation flow (/api/adapt-case-study) • Improve case study scoring algorithm • Refine coaching chat prompts and AI evaluation quality • Test case study recommendation accuracy against user context | #9 Adaptation flow #6 Coaching chat polish | Not Started
12 | Mar 6 | Thu | Full Flow + Polish | • Accessibility check: keyboard nav, screen reader, color contrast • Mobile responsiveness pass on all components • Performance optimization: API response times, lazy loading • Security pass: input sanitization, API key handling | Accessibility + security | Not Started
13 | Mar 9 | Mon | Testing | • Run 15-20 full end-to-end test sessions • Test full coaching flow: assessment → AI eval → coaching → reflection → PDF • Test chatbot with diverse questions • Test case study search, filter, and adaptation • Document all bugs: P0 / P1 / P2 | E2E testing | Not Started
14 | Mar 10 | Tue | Testing | • Fix P0 and P1 bugs • AI accuracy evaluation: test coaching quality across question types • Test with simulated concurrent sessions • Expand test suite coverage for new components | Bug fixes + AI eval | Not Started
15 | Mar 11 | Wed | Testing | • Beta test with 3-5 InnovateUS users • Observe and collect feedback on coaching flow • Test case study relevancy and recommendations • Fix critical issues found during beta | Beta testing | Not Started
16 | Mar 12 | Thu | Deploy | • Implement critical beta feedback • Deploy to production (Render) • Run smoke tests on production URL • Final content review: all copy, questions, labels | Deploy to production | Not Started
17 | Mar 13 | Fri | Deploy | • Final QA pass on production • Build demo: screen recordings, walkthrough, key metrics • Create/update technical documentation & setup guide • Update README.md to reflect current architecture | Final QA + demo prep | Not Started
18 | Mar 16 | Mon | Buffer | • Emergency bug fixes • Practice demo presentation • Prepare handoff documentation • PROTOTYPE COMPLETE — ready for pilot | Buffer / handoff PROTOTYPE DONE | Not Started
TOTAL |  |  | 18 days | Strategy: OpenAI GPT-4.1 + Weaviate RAG from day one → Express backend → Render deploy

## Tech Stack
Tech Stack — Current Implementation
Strategy: Built on OpenAI + Weaviate RAG from day one. Migrated from Netlify to Express in Week 2.
Category | Using | Why | Status | Alternatives Considered
Frontend | React 18 + Vite 6 + Tailwind CSS 4 + TypeScript | Fast build, type safety, rapid styling, modern tooling | Confirmed | Next.js, plain HTML
UI Components | Radix UI (Dialog, Tabs, ScrollArea, Select, Tooltip) | Accessible, unstyled primitives, composable with Tailwind | Confirmed | shadcn/ui, MUI, Chakra UI
Icons | Lucide React | Lightweight, consistent, tree-shakeable icon set | Confirmed | Heroicons, FontAwesome
Markdown Rendering | react-markdown + remark-gfm | Rich content display for AI responses, GFM table support | Confirmed | MDX, marked
PDF Export | jsPDF | Client-side PDF generation for reflection reports | Confirmed | html2pdf, Puppeteer
Routing | React Router 7 | Standard React routing with nested routes | Confirmed | TanStack Router
Backend | Express 5 (Node.js) | Simple REST APIs, SSE streaming support, JS end-to-end | Confirmed | Netlify Functions (abandoned), FastAPI
Vector Database | Weaviate (Cloud) | Hybrid search (BM25 + vector), built-in OpenAI vectorizer module | Confirmed | Pinecone, Qdrant, ChromaDB
AI / LLM | OpenAI GPT-4.1 / GPT-4.1-mini | High quality coaching responses, function calling for agent tools | Confirmed | Claude, Gemini
Embeddings | text-embedding-3-small (via Weaviate) | Cost-efficient, good quality, integrated with Weaviate vectorizer | Confirmed | text-embedding-3-large
PDF Ingestion | Docling (Python) + custom Node.js pipeline | PDF → Markdown → LLM-based chunking → Weaviate | Confirmed | LangChain, LlamaIndex
Excel Ingestion | pandas + openpyxl (Python) | Participedia case study data from Excel → Weaviate | Confirmed | SheetJS
Testing | Vitest + @testing-library/react + jsdom | Fast Vite-native testing with component testing | Confirmed | Jest, Playwright
Hosting | Render | Auto-deploy, supports Express server, free tier available | Planned | Vercel, Railway, Netlify
Dev Tools | Weaviate MCP (Cursor integration) | Direct DB queries and schema inspection from IDE | Confirmed | Weaviate Console
KEY DECISION: Migrated from Netlify Functions to Express on Feb 20 for better SSE streaming, simpler deployment, and unified server.

## Feature Tracker
Core Features — Completion Tracker (includes 1 pivoted)
# | Feature | Target Phase | Target Done By | Status
1 | Knowledge base ingestion (PDF + Excel → Weaviate) | Ingestion Pipeline | Feb 18 | Completed
2 | RAG Chatbot with SSE streaming & source citations | Backend Integration | Feb 19 | Completed
3 | Full React UI (Home, Coach, Case Studies, Layout) | UI Build | Feb 17 | Completed
4 | Agent system (function calling, tool loop, hybrid search) | Backend Integration | Feb 19 | Completed
5 | Nesta 9-question coaching assessment + AI evaluation | Coach Flow Redesign | Mar 3 | Completed
6 | Per-question coaching chat panel | Coach Flow Redesign | Mar 3 | Completed
7 | Reflection page with PDF export | Coach Flow Redesign | Mar 3 | Completed
8 | Case study library (browse, filter, detail view) | Backend Integration | Feb 19 | Completed
9 | Case study AI adaptation ("Adapt to my situation") | Backend Integration | Feb 20 | Completed
10 | Engagement plan generator (questionnaire → follow-ups → plan) — PIVOTED to coaching flow | Backend Integration | Feb 20 | Pivoted
11 | Relevancy scoring for case studies | Migration & Testing | Feb 20 | Completed
12 | Search bar + topic filtering for case studies | Refinement | Feb 23 | Completed
13 | InnovateUS UI branding & theming | Migration & Testing | Feb 20 | Completed
14 | Test suite (component tests for all major views) | Migration & Testing | Feb 20 | Completed
15 | Deployment configuration (Render) | Refinement | Feb 23 | Started

## Phase Summary
Phase Summary
Phase | Dates | Days | What Got / Gets Done | Milestone
Setup & Research | Feb 9 | 1 | Repo setup, architecture decisions, license, .gitignore, initial README | Dev environment ready, repo initialized
Ingestion Pipeline | Feb 10–11 | 2 | PDF ingestion, LLM-based chunking, Weaviate schema, Docling PDF→MD, basic chatbot UI | Documents ingested into Weaviate, chatbot functional
UI Build | Feb 17 | 1 | Full React app with all pages, Radix UI component library, routing, Nesta assessment, Tailwind styling | Complete frontend scaffold with all views
Data Ingestion & Backend | Feb 18–19 | 2 | Excel pipeline, case study data, RAG agent tools, agent runner, wired UI to backend, chunking adjustments | Full-stack app: UI connected to RAG backend
Migration & Testing | Feb 20 | 1 | Netlify → Express migration, test suite, relevancy scoring, InnovateUS branding, markdown rendering | Express server live, tests passing, branded UI
Refinement & Deploy Config | Feb 23 | 1 | Search & filter for case studies, Render.yaml, output formatting | Case study discovery improved, deploy config ready
Coach Flow Redesign | Mar 3 | 1 | Multi-step coaching: Assessment → Dashboard → Coaching Chat → Reflection, PDF export, new routes | Complete AI coaching pipeline working
Full Flow + Polish | Mar 4–6 | 3 | End-to-end integration, UX polish, accessibility, security, performance, coaching flow & case study refinement | Participant flow polished & secure
Testing + Deploy | Mar 9–13 | 5 | E2E testing, bug fixes, beta with InnovateUS users, production deploy, demo preparation | All 15 features verified in production
Buffer | Mar 16 | 1 | Emergency fixes, demo practice, handoff docs | PROTOTYPE COMPLETE

## Deliverables
Summary of Deliverables — For Review by Beth & Advisors
# | Deliverable | Description / What to Review | Ready By | Type | Reviewer | Status
1 | Project Plan & Timeline | Daily plan, tech stack, feature list, phase breakdown. Confirms scope, timeline, and division of work across Kushal, Manan, and Batuhan. | Feb 9 | Document | Beth, Ani, David | Completed
2 | Knowledge Base Pipeline | Working PDF + Excel ingestion into Weaviate. LLM-based intelligent chunking with review loop, hybrid BM25 + vector search. Participedia case studies loaded. | Feb 18 | Technical Demo | Beth, Ani, David | Completed
3 | RAG Chatbot Demo | Floating Q&A chatbot: SSE streaming, source citations, contextual answers from knowledge base. Demonstrates retrieval quality. | Feb 19 | Demo / Gate | Beth, Ani, David | Completed
4 | Full UI Prototype | React app with all pages: Home, Coach (9 Nesta questions), Case Studies (browse/filter/detail), ChatBot. InnovateUS branding applied. | Feb 20 | Demo / Gate | Beth, Ani, David | Completed
5 | Express Migration & Test Suite | Backend migrated from Netlify Functions to Express. All API endpoints working. Component tests for Home, Layout, Coach, ChatBot, CaseStudies. | Feb 20 | Technical Milestone | Beth, Ani, David | Completed
6 | Case Study Library with Search | Case studies from Weaviate with topic filtering, search bar, relevancy scoring, and AI adaptation flow ("Adapt to my situation"). | Feb 23 | Demo / Gate | Beth, Ani, David | Completed
7 | AI Coaching Flow | Complete multi-step flow: 9-question Nesta assessment → AI evaluation (addressed/partial/not-addressed) → per-question coaching chat → reflection with PDF export. | Mar 3 | Demo / Gate | Beth, Ani, David | Completed
8 | Engagement Plan Generator (Pivoted) | Originally built as questionnaire → follow-up questions → structured plan. Pivoted to the Nesta coaching flow which provides more structured, per-question AI coaching with assessment evaluation and reflection. | Feb 20 | Pivoted Feature | Beth, Ani, David | Pivoted
9 | Polished Participant Experience | Accessibility (WCAG 2.1 AA), mobile responsiveness, security (input sanitization, API key handling), performance optimization. | Mar 6 | Review / Gate | Beth, Ani, David | Not Started
10 | E2E Test Results | Summary of 15-20 end-to-end test sessions across devices. Bug documentation (P0/P1/P2) and resolution status. | Mar 10 | Report | Beth, Ani, David | Not Started
11 | Beta Test Results | Feedback from 3-5 InnovateUS beta users: usability, coaching quality, completion flow, pain points, improvements made. | Mar 11 | Report | Beth, Ani, David | Not Started
12 | Production Deployment | Prototype live on Render production URL. All 15 features verified. Smoke test results. | Mar 12 | Milestone | Beth, Ani, David | Not Started
13 | Demo Package | Live walkthrough script, screen recordings of coaching flow + case studies + chatbot, architecture diagram, AI quality metrics. | Mar 13 | Presentation | Beth, Ani, David | Not Started
14 | Technical Documentation | Updated README, API docs, architecture overview, deployment instructions, environment config guide. Everything needed to maintain the system. | Mar 13 | Document | Beth, Ani, David | Not Started
15 | Final Prototype Handoff | Working production URL, source code repo, documentation, test results, demo materials. Ready for pilot with InnovateUS cohort. | Mar 16 | Final Handoff | Beth, Ani, David | Not Started
GATES = Checkpoints where advisor go/no-go feedback is needed before proceeding to the next phase